## EXAMPLE Risk Register
Simple Risk Register Template Example
Auto-calculates
Risk ID | Risk Description | Impact Description | Impact Level Rate 1 (LOW) to 5 (HIGH) | Probability Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Probability Address the highest first. | Mitigation Notes | Status | Owner | Date Identified | Last Reviewed | Notes
SAF-001 | Wet floor near the loading bay | Slip, minor injury | 2 | 1 | 2 | Post signage, mop the area daily | Open | Lori Garcia | 2031-01-05 | 2031-01-08 | Near door 2
SAF-002 | Low overhead beam | Head bump hazard | 3 | 2 | 6 | Foam padding, warning tape | In Progress | Makara McLean | 2031-01-06 | 2031-01-10 | Truck crew flagged
SAF-003 | Broken step on scaffolding | Fall from height | 2 | 3 | 6 | Replace the damaged plank | Escalated | Marta Hicks | 2031-01-07 | 2031-01-09 | Reported by the safety audit
SAF-004 | Loose cables near the control room | Trip hazard | 1 | 4 | 4 | Cable matting ordered | In Progress | Mateus Tobin | 2031-01-09 | 2031-01-11 | Short-term fix used
SAF-005 | Forklift blind corner | Collision potential | 1 | 5 | 5 | Add a convex mirror | Open | Olivia Carter | 2031-01-10 | 2031-01-12 | High-traffic zone
SAF-006 | Chemical storage mislabeled | Exposure risk | 2 | 4 | 8 | Relabel, safety training refresh | Open | Petrus Nishimura | 2031-01-11 | 2031-01-12 | Two bins affected
SAF-007 | Ventilation fan not working | Heat buildup in the work area | 5 | 3 | 15 | Temp fan in use, part on order | In Progress | Raghu Prakash | 2031-01-12 | 2031-01-13 | Summer risk
SAF-008 | Broken PPE dispenser | Access delay for gloves | 6 | 2 | 12 | Order a new unit | Closed | Romy Bailey | 2031-01-13 | 2031-01-15 | Resolved 01/14
SAF-009 | Unsecured ladder during setup | Fall potential | 2 | 1 | 2 | Locking base added | Closed | Sarah Goodwin | 2031-01-14 | 2031-01-17 | Training reminder sent
SAF-010 | Dust accumulation near vents | Respiratory irritation | 4 | 2 | 8 | Scheduled deep clean | In Progress | Sasha Petrov | 2031-01-15 | 2031-01-18 | Vendor scheduled 01/20
SAF-011 | Noise levels exceed 85 dB | Hearing loss over time | 3 | 3 | 9 | Enforce ear protection | Open | Lori Garcia | 2031-01-16 | 2031-01-19 | Random spot checks
SAF-012 | Power tool left plugged in | Electrocution risk | 2 | 4 | 8 | Daily end-of-shift checks | Open | Makara McLean | 2031-01-17 | 2031-01-18 | Reminder signage added
SAF-013 | Untrained temp worker | Incorrect machine use | 2 | 5 | 10 | Shadow shifts added | In Progress | Marta Hicks | 2031-01-18 | 2031-01-20 | Onboarding revised
SAF-014 | Oil spill on the walkway | Slip, twisted ankle | 2 | 5 | 10 | Immediate cleanup protocol | Closed | Mateus Tobin | 2031-01-19 | 2031-01-21 | Logged in site report
SAF-015 | No emergency light in storage | Navigation issue in blackout | 1 | 4 | 4 | Install a backup light | Open | Olivia Carter | 2031-01-20 | 2031-01-23 | Checked wiring
SAF-016 | Loose handrail on stairs | Loss of balance risk | 2 | 4 | 8 | Tightened and retested | Closed | Petrus Nishimura | 2031-01-21 | 2031-01-22 | QA sign-off complete
SAF-017 | Leaking pipe above walkway | Slip, fall hazard | 3 | 3 | 9 | Leak patched, floor mat placed | In Progress | Raghu Prakash | 2031-01-22 | 2031-01-25 | Monitor for recurrence
SAF-018 | Faulty fire alarm sensor | Delayed alert in an emergency | 4 | 2 | 8 | Vendor notified | Escalated | Romy Bailey | 2031-01-23 | 2031-01-26 | Recheck 01/28
SAF-019 | The stack of pallets is unstable | Tip-over hazard | 2 | 1 | 2 | Re-stack, add safety straps | Open | Sarah Goodwin | 2031-01-24 | 2031-01-27 | Observed near dock B
SAF-020 | Debris near the forklift route | Obstruction hazard | 2 | 4 | 8 | Assign cleanup daily | In Progress | Sasha Petrov | 2031-01-25 | 2031-01-27 | End-of-day checklist updated
SAF-021 | Exit sign flickering | Visibility issue | 1 | 4 | 4 | Replace the LED unit | Closed | Lori Garcia | 2031-01-26 | 2031-01-27 | Completed 01/26

## BLANK Risk Register
Simple Risk Register Template
Auto-calculates
Risk ID | Risk Description | Impact Description | Impact Level Rate 1 (LOW) to 5 (HIGH) | Probability Level Rate 1 (LOW) to 5 (HIGH) | Priority Level Impact x Probability Address the highest first. | Mitigation Notes | Status | Owner | Date Identified | Last Reviewed | Notes | KEY
|  |  | 1 | 1 | 1 | [6 empty] | LEVEL
|  |  | 2 | 2 | 4 | [6 empty] | 1
2
3
4
5

## Scale and Key
RISK REGISTER SCALE
P R O B A B I L I T Y | 5 | 5 | 10 | 15 | 20 | 25 | Status
| 4 | 4 | 8 | 12 | 16 | 20 | Open
| 3 | 3 | 6 | 9 | 12 | 15 | In Progress
| 2 | 2 | 4 | 6 | 8 | 10 | Closed
| 1 | 1 | 2 | 3 | 4 | 5 | Escalated
|  | 1 | 2 | 3 | 4 | 5
I M P A C T